## Sheet1
Project | Code | PM | Assets Needed | Status | Web | Launch | Markeitng List
CML Video Case - O’Brien | PI4VOT031 | Meg | ACD | Edits with web | Steven | 2014-10-24
National Grand Rounds - Tulane | PI4LGR034 | Meg | ACD | Approved with release date change. Eblast requested. | Tim
Tampa Webcast |  | Debbie | ACD | Video edits provided by Tim 10/03. Slides, Timings, CME links, segmentation received 10/27.
ETA Expert Review DTC | PI4VVR059 |  | slides by 10/15 | awaiting final approval 10/28 and itunes podcast refresh | Ben | 2014-10-17
ESGO PDS |  | Elisa | final approval | Live on site 10/23. Elisa sent edits 10/25 | Tim | 2014-10-20
ESMO GEP NETS Webcast |  | Saskia | final approval | Edits made and routed 10/29 | Tim
ESMO Biosimilars Webcast |  |  | edits | Routed 10/29 | Tim
ESMO Breast Webcast |  |  | slides, timings | ACD received 10/24 | Ben
ESMO CINV |  | saskia | cme links | Routed 10/29 | Grace
ESMO Ovarian Webcast |  | saskia | nothing | timings and ACD received
ESMO VJC |  | meg | nothing | ACD and slides with web
EANO webcast |  | elise | slides, timings | ACD with web
Rush U Grand Rouds live page |  | debbie | nothing | ACD with web
CML Rounds eblast |  |  |  | ACD with web | Tim | 2014-10-31
ESMO VPS - Ramalingam |  | meg |  | All materials with web |  | 2014-10-31
ESMO ER CRC |  | meg | ACD | Slides, CME links with web
ESH PV PDS |  | saskia | ACD | slides

## Completed
PLATO Fellows Forum | PI4LOT033 | Webcast |  |  | web pages approved. final edits with web | Lisa
ASCO Prostate Flashcard e-blast |  | Email
ASCO CLL iNHL Flash Card E-Blast |  | Email
West Clinic PDS | PI4LMS047 | PDS
ECOP HER2 Breast Cancer | PB4LSS050 | PDS
VJC PV | PI4VVJ065 | VJC
Melanoma Congress Webcast | PB4LCN025 | webcast | Elise VS |  | Web page live. Eblast edits in production | Paul
ESH PV Live Page |  | Live Meeting | Saskia | 2014-09-15 | changes routed for review 9/17 | Lisa