## Sheet1
Project | Code | PM | Assets Needed | Status | Web | Launch | Markeitng List
Tampa Webcast - Moffit |  | Debbie | nothing | in production 11/10 est review 11/11 | Tim | route 11/11
ETA Expert Review DTC | PI4VVR059 |  | nothing | live on site. Eblast approved. | Ben | Eblast on hold
ESMO GEP NETS Webcast |  | Saskia | final approval | awaiting final approval 11/12 | Tim
ESMO Biosimilars Webcast |  |  | edits | live pending Sugar. Awaiting eblast approval 11/11 | Tim
ESMO Breast Webcast |  |  | reference link | awaiting approval 11/11 | Ben
ESMO CINV |  | saskia | nothing | 1 eblast change needed | Grace
ESMO Ovarian Webcast |  | saskia | nothing | eblast approved 11/11 | Tim
ESMO VJC NSCLC |  | meg | client edits to come in Wed | routed 10/30. video edit and segmentation edits 11/10 | Paul
EANO webcast |  | elise | slides, timings | awaiting cme and add't edits 11/12 | Tim
ESMO VPS - Ramalingam |  | meg | nothing | awaiting approval 11/10 | Tim | 2014-10-31
ESH PV PDS |  | saskia | nothing | awaiting feedback 11/12 | Ben
CTOS PDS |  | Jae/Rinath | edits | small changes in production | Tim and Ben | 2014-11-05
ER ALL |  | meg | everything |  |  | 2014-11-20
ESMO VJC EBC |  | meg | slides, CME | ACD with Web
GBM PDS |  | Meg | ACD | Slides with web 11/10
Chemo found PDS |  | Meg | ACD | Slides on S3 |  | 2014-11-18
SABCS Live |  |  |  | Routed 11/11
IGCS PDS |  |  | slides | ACD with web 11/12 |  | 2014-11-18
ESMO VPS eblast |  |  |  | awaiting approval 11/04 | Paul
ER DTC eblast |  |  |  | routed 11/04 | Paul | Asked for update 11/07
ESMO Ovarian eblast |  |  |  | in production 11/07 | Paul
ESMO Biosimilars Webcast |  |  |  | in production 11/07 | Paul

## Completed
PLATO Fellows Forum | PI4LOT033 | Webcast |  |  |  |  | web pages approved. final edits with web | Lisa
ASCO Prostate Flashcard e-blast |  | Email
ASCO CLL iNHL Flash Card E-Blast |  | Email
West Clinic PDS | PI4LMS047 | PDS
ECOP HER2 Breast Cancer | PB4LSS050 | PDS
VJC PV | PI4VVJ065 | VJC
Melanoma Congress Webcast | PB4LCN025 | webcast | Elise VS |  |  |  | Web page live. Eblast edits in production | Paul
ESH PV Live Page |  | Live Meeting | Saskia |  | 2014-09-15 |  | changes routed for review 9/17 | Lisa
CML Video Case - O’Brien | PI4VOT031 | Meg | ACD | launched. Eblast edits with web 10/31 | Steven/Paul | 2014-10-24
ESMO ER CRC |  | meg | nothing | live on site. Eblast routed 10/31 | Grace
National Grand Rounds - Tulane - New Orleans | PI4LGR034 | Meg | ACD | Approved with release date change. Eblast requested. Waiting for further instruction on eblast. | Tim
Rush U Grand Rouds live page |  | debbie | nothing | approved 11/03. eblast in production | Ben
rush U eblast |  |  |  | approved | Paul
ESGO PDS |  | Elisa | final approval | Eblast sent | Tim | Eblast on hold