## Sheet1
Project | Code | PM | Assets Needed | Status | Web | Launch | Markeitng List
CML Video Case - O’Brien | PI4VOT031 | Meg | ACD | launched/ eblast being created | Steven | 2014-10-24
National Grand Rounds - Tulane - New Orleans | PI4LGR034 | Meg | ACD | Approved with release date change. Eblast requested. Waiting for further instruction on eblast. | Tim
Tampa Webcast - Moffit |  | Debbie | ACD | Video edits provided by Tim 10/03. Slides, Timings, CME links, segmentation received 10/27.
ETA Expert Review DTC | PI4VVR059 |  | slides by 10/15 | awaiting final approval 10/28 and itunes podcast refresh | Ben | 2014-10-17
ESGO PDS |  | Elisa | final approval | Live on site 10/23.Awaiting final approval for eblast 10/28. | Tim | 2014-10-20
ESMO GEP NETS Webcast |  | Saskia | final approval | one support edit 10/30, awaiting Christine's approval | Tim
ESMO Biosimilars Webcast |  |  | edits | Routed 10/30 | Tim
ESMO Breast Webcast |  |  | slides, timings | ACD received 10/24 setting up videos for what we have. | Ben
ESMO CINV |  | saskia | cme links | Routed 10/29 | Grace
ESMO Ovarian Webcast |  | saskia | nothing | timings and ACD received | Tim
ESMO VJC NSCLC |  | meg | nothing | ACD and slides with web | Paul
EANO webcast |  | elise | slides, timings | ACD with web
Rush U Grand Rouds live page |  | debbie | nothing | routed on 10/28 | Ben
CML Rounds eblast |  |  |  | routed 10/29 | Tim | 2014-10-31
ESMO VPS - Ramalingam |  | meg | slides | awaiting slides | Tim | 2014-10-31
ESMO ER CRC |  | meg | nothing | everything with Web | Grace
ESH PV PDS |  | saskia | ACD | slides
CTOS PDS |  | Jae | nothing | everything with Web | Tim and Ben | 2014-11-05
ER ALL |  | meg | everything
ESMO VJC EBC |  | meg | everything
ESMO VPS eblast |  |  |  |  | Paul
O'Brien CML Case eblast |  |  |  |  | Paul

## Completed
PLATO Fellows Forum | PI4LOT033 | Webcast |  |  | web pages approved. final edits with web | Lisa
ASCO Prostate Flashcard e-blast |  | Email
ASCO CLL iNHL Flash Card E-Blast |  | Email
West Clinic PDS | PI4LMS047 | PDS
ECOP HER2 Breast Cancer | PB4LSS050 | PDS
VJC PV | PI4VVJ065 | VJC
Melanoma Congress Webcast | PB4LCN025 | webcast | Elise VS |  | Web page live. Eblast edits in production | Paul
ESH PV Live Page |  | Live Meeting | Saskia | 2014-09-15 | changes routed for review 9/17 | Lisa