## Sheet1
Project | Code | PM | Assets Needed | Status | Web | Launch | Markeitng List
CML Video Case - O’Brien | PI4VOT031 | Meg | ACD | launched. Eblast edits with web 10/31 | Steven/Paul | 2014-10-24
National Grand Rounds - Tulane - New Orleans | PI4LGR034 | Meg | ACD | Approved with release date change. Eblast requested. Waiting for further instruction on eblast. | Tim
Tampa Webcast - Moffit |  | Debbie | ACD | Video edits provided by Tim 10/03. Slides, Timings, CME links, segmentation received 10/27.
ETA Expert Review DTC | PI4VVR059 |  | nothing | live on site. Eblast in production | Ben | 2014-10-17
ESGO PDS |  | Elisa | final approval | Live on site 10/23.Awaiting final approval for eblast 11/03. | Tim | 2014-10-20
ESMO GEP NETS Webcast |  | Saskia | final approval | live. Email routed 11/03 | Tim
ESMO Biosimilars Webcast |  |  | edits | awaiting final approval 11/03 | Tim
ESMO Breast Webcast |  |  | reference link | Edits made. Will be routed today | Ben
ESMO CINV |  | saskia | nothing | Awaiting final approval 10/31 | Grace
ESMO Ovarian Webcast |  | saskia | CME links | edits with web 11/03. awaiting cme. Will route 11/03 | Tim
ESMO VJC NSCLC |  | meg | client edits to come in Wed | routed 10/30 | Paul
EANO webcast |  | elise | slides, timings | in production 11/04 | Tim
Rush U Grand Rouds live page |  | debbie | nothing | approved 11/03. eblast in production | Ben
CML Rounds eblast |  |  |  | routed 10/29 | Tim | 2014-10-31
ESMO VPS - Ramalingam |  | meg | slides | awaiting slides | Tim | 2014-10-31
ESMO ER CRC |  | meg | nothing | live on site. Eblast routed 10/31 | Grace
ESH PV PDS |  | saskia | ACD | slides
CTOS PDS |  | Jae | edits | routed 11/03 | Tim and Ben | 2014-11-05
ER ALL |  | meg | everything |  |  | 2014-11-20
ESMO VJC EBC |  | meg | everything
ESMO VPS eblast |  |  |  | routed 10/31 | Paul
O'Brien CML Case eblast |  |  |  | routed 10/31 | Paul

## Completed
PLATO Fellows Forum | PI4LOT033 | Webcast |  |  | web pages approved. final edits with web | Lisa
ASCO Prostate Flashcard e-blast |  | Email
ASCO CLL iNHL Flash Card E-Blast |  | Email
West Clinic PDS | PI4LMS047 | PDS
ECOP HER2 Breast Cancer | PB4LSS050 | PDS
VJC PV | PI4VVJ065 | VJC
Melanoma Congress Webcast | PB4LCN025 | webcast | Elise VS |  | Web page live. Eblast edits in production | Paul
ESH PV Live Page |  | Live Meeting | Saskia | 2014-09-15 | changes routed for review 9/17 | Lisa